## Sheet1
Shipley Town Council - Climate Action Plan | [7 empty] | Agreed | October | 2023
Jury Recommendation |  |  |  | Town Council Plan - to be explored
Priority/ Score (out of 42) | Area | Recommendation | Suggested Actions | Additional / Alternative Actions to be explored | Other Stakeholders to Collaborate and Communicate With | Lead Responsibility | Budget requirement £ | Source of Funds | Timescale (short, medium or long) | Target Completion Date
1 Score 37 | Housing | Facilitate the retrofitting of Shipley’s homes and buildings to maximise their energy efficiency | 1. campaign to increase awareness, raise interest and share experiences of retrofitting via physical or online ‘One Stop Retrofit Shop' | Raise trade awareness also | Above Ground (Andrew Gardener) To Walk Project (Steve Hoffman) Incommunities Housing Building Trade Associations Pure House People Powered Retrofit (Manchester) | CE&EC (Councillor McHugh) |  | highlight positive impacts on health and household budgets to save £ and potentially fund | Medium | 2024-03-03
|  |  | 2. work with local education providers e.g. Shipley College to develop and incentivise a range of courses on retrofitting | Establish what already offered | Shipley, Keighley and Bradford Colleges | CE&EC (Councillor Parkinson) |  |  | Short | 2023-10-01
3. liaise with WYCA and other retrofitting funding streams to facilitate Shipley’s appetite for green jobs
|  |  | 4. encourage landlords to ensure rental homes in Shipley are minimum C energy rating or above | start with public landlords until national directive (5) acheived Use info generated at (1) | Incommunities Housing | CE&EC (Councillor McHugh) |  |  | Medium | 2024-03-01
|  |  | 5. lobby central government for energy efficiency standards to be incorporated in regulations | Include in Bradford's: Design Code (a pathfinder project) Local Plan (next iteration) Development Framework | Phillip Davies MP to be asked to write to Minister asking that German passive house standards be adopted in the UK | CE&EC (Councillor Parkinson) with Planning & Regeneration Committee (Councillor Watson) |  |  | Short | 2023-10-01
2 Score 35 | Nature | Encourage/enable nature to thrive in Shipley by securing council funds and external grants to support environmental action. Public participation encouraged to support actions providing sanctuary and sustenance for insects. | 6. seek funds to create pollinator corridor of private and shared garden spaces that bridge communities living in affluent and more deprived areas. | Raise public/partner awareness of pollinators and encourage planting Saltaire Road pollinator corridor established July 23 Extend planters on tarmac areas (use of cotonesta?) Plant trees Influence Towns Fund planting | STC A&GSC Shipley in Bloom Incommunities Mens Shed CBMDC STC (P&RC) Nifty Sustainability green spaces bid | STC A&GSC | £500 £500 | Shipley in Bloom for seed and plant distribution, wood for planters Grant required for trees (and planting permissions) | medium | 2024-05-01
|  |  | 7. manage public spaces in a nature friendly way; community planters, reduced mowing, stopping use of pesticides and insecticides, saving trees and hedges, encouraging beehives. | Allotments under STCs direct control Pilot relaxed mowing and glyphosate free trials in Shipley parks | Shipley in Bloom Friends of Northcliffe CBMDC InCommunities | STC A&GSC | 500 | A&GSC for signage in pilot areas | short | 2023-09-01
3 Score 35 | Education | Create an information hub (physical and/or online) where local people can go for information and advice | 8. Rotating displays in Library, underground market …………pop up events | Digital - STC website page Physical - ?Wilko premises Utilise notceboards, especially outside Town Hall Advertising campaign pointing to digital and physical hub (Steve to share graphics) | Multi organisation working group including Plastic Free Shipley, Friends of the Earth, etc (PM raise at GBGW meeting 12 September) Library DIY SOS to create/showcase skills | CE&EC STC Comms Lead | rent for premises / staff printing of display materials |  | Short Medium Long | Nov 23 - produce and mount some public displays March 24 - premises funding identified March 25 - hub running
|  |  | 9. energy saving tips | to include retrofit info
10. Ideas for being more environmentally friendly
|  |  | 11. host seed bank |  | Veg on the Edge Allotment holders | A&GSC
|  |  | 12. signpost public to local schemes and organisations |  |  | Communications Lead
4 Score 34 | Transport | Create a vision for transport to reduce car use and increase active travel | 13. Ask all councils to advocate integrated public transport systems that reduce carbon, particulates, nitrogen oxides (NOx) and sulphur oxides (SOx) in our local urban landscapes) | Invite Susan Hinchliffe (Bradford Council) and Tracy Brabin (WYCA) to attend CE&EC Write to CBMDC for details of relevant plans Area Committee accepted Citizen's Jury Report and have forwarded it to WYCA, Bradford Council Executive and range of other committees (Councillor Watson to act as link) | Active Travel Hub Bradford Shipley Travel Alliance CBMDC WYCA | CE&EC (Deputy Town Clerk) |  |  | short (for updates) | 2023-11-01
|  |  | 14. give greater priority to pedestrian/people powered transport inc designated safe travel zones/routes to improve physical/mental health and reduce carbon emissions | Bradford / Bingley Road scheme - Shipley Town Council to request presentation | Living Streets Active Travel Zones Bradford Shipley Travel Alliance National Planning Regulations | P&RC |  |  | Short (to presentation) Long (to implement) | Dec 23 March 27
|  |  | 15. Shipley e-bike (and/or scooter) hire scheme | established | Active Travel Hub WYCA/CBMDC |  |  | WYCA grant STC | short | 2023-06-01
|  |  | 16. improve public transport signage |  | Towns Fund (Councillor Connors) Network Rail | P&RC |  |  | Medium | 2023-10-24
|  |  | 17. subsidise ticket costs for vulnerable groups | establish what already offered | WYCA - mayor's fares West Yorkshire concessionary tickets Metro | CE&EC (Councillor Parkinson) |  |  | short | 2023-10-01
|  |  | 18. research barriers to giving up the car to inform Active Travel Scheme | Divorce Your Car (To Walk Project) - lead to local campaign researching barriers | Bradford Shipley Travel Alliance report (Phillippa Bannister) to inform the work of Shipley's Active Travel Hub | CE&EC |  |  | Medium | 2024-03-01
|  |  | 19. regular publishing of Clean Air Zone data inc impact on HGV traffic |  | Invite Sally Jones, CBMDC, to present data and discuss publication and (20) | Reported at STC CE&EC |  |  | Short | 2023-11-01
|  |  | 20. request CAZ charge funds support jury’s recommendations |  | CBMDC | CE&EC
|  |  | 21. encourage greater numbers of electric buses |  | WYCA - write and ask for detail of plans | CE&EC |  |  | Short | 2023-11-01
|  |  | 22. utilise Citizens’ Juries to redesign public and private transport networks to maximise benefits to public health and environment. | Publicise Shipley's experience and outcomes nationally Offer tips and support to others organising CJs Juror's Experience Report (Jen Dyer) Attend and support report when considered at Bradford Council and WYCA meetings | WYCA MP | CE&EC |  |  | Short | 2023-12-01
5 |  | Incentivise and encourage Shipley businesses to limit their climate impact. | businesses make Yorkshire & Humber Climate Action Pledge, or similar to 23. improve insulation rating of their buildings | Reduce single use plastics e.g. Borrow Bradford Incorporate business info in hub | Rotary Club of Shipley (in absence of BID, forum, etc) Shipley Active Travel Hub building, Windsor Court Green Street Public toilets | CE&EC (personal approach required) STC to support local businesses Needs dedicated Working Group |  |  | Medium | 2024-03-01
|  |  | 24. invest in region's natural assets | Switch to LED lightbulbs |  | " |  |  | Long | 2025-12-01
|  |  | 25. use fossil fuel free energy generation |  | Target large employers: NHS / GP Practices Incommunities Shipley College Metal Box (Adam Clerking, Chair of Towns Fund Board) | " |  |  | " | "
|  |  | 26. cut emissions at pace advised in IPCC report |  | " | " |  |  | " | "
|  |  | 27. adopt cycle to work schemes. |  | " | " |  |  | Medium | 2024-03-01
6 Score 31 | Education | Embed a Climate Change Curricula in Schools that helps learners of all ages address and adapt to climate change. | 28.review current curriculum taught in local primary and secondary schools |  |  | STC CE&EC Saltaire - ?Jody Harris Wycliffe - Councillor Parkinson Shipley CofE - ? St Walburgers - ? |  |  | Short | 2023-12-01
|  |  | 29. convene knowledge exchange workshops with local schools/wider education departments to identify ways to embed specific teaching and resources in the school curriculum (specifically Sarah Fishwick, Leeds Development Education who spoke to Jury) that engages students and their families | Fund 2 places per Shipley primary school on scheme to train teachers online independent learning for primary school £25 per teacher to undertake the course Taught course £95 Establish interest - Anna to advise | Leeds Development Education (Sarah Fishwick) Nifty Sustainability | CE&EC (Councillor Parkinson) | £800 (£90 per place) | STC CE&EC climate budget | Medium | 2024-07-01
|  |  | 30.support Youth Climate Assembly to capture views, experiences and ideas of under 18s (not yet able to vote) | Pop up events comparing awareness in eco primary to non eco primary school Climate crisis workshop on anxiety | Nifty Sustainability KT Shepherd Permaculture | CE&EC | £ ? |  | Medium | 2024-03-01
|  |  | 31.explore partnerships (e.g. Otley 2030 and Solar 4 Schools) to generate non fossil fuel energy on school buildings |  | Bradford Community Energy Bradford Council/ Academy Trusts - school premises Cllr Warnes Friends of the Earth Baildon school Community Assembly group | Councillor McHugh & Farren |  | Grant available | Long | 2023-03-25
7 Score 31 | Transport | Encourage more people to walk by making it easier and safer. | 32.improve pedestrian crossing over Otley Rd from Kirkgate to (train) Station Road | Phase crossing to go green at same time | CBMDC - Highways Ward Councillors ? Town Fund Notes of recent meeting with Simon D'vali? |  | £? |  | Long | 2023-03-26
|  |  | 33.install more street lighting to ensure visibility and safety of pedestrians whilst specifically drawing on light pollution sensitive street light design | Ongoing scheme explore solar powered lighting on canal towpath | Scope particular locations that are problematic and keep a log ?sculpture trail along river bank | CE&EC / P&RC - carefully worded social media poll | £? |  | Short (scoping) Long (implementation) | Nov-23 Mar-26
|  |  | 34. hold events to promote walking in Shipley | Enrol Shipley in “walkers welcome" scheme Living Streets to promote utility walking To Walk project - Steve Hoffman Walk/Cycle/Scoot to School promotion | Active Travel Hub Northcliffe Park Womens Institute Establish Walking Workshop to take forward | Councillor Parkinson + volunteers |  |  | Medium | 2023-03-25
|  |  | 35.join canal towpath and Greenway into Bradford | Write to CBMDC re "missing link" link to train station | CBMDC - Heritage Officer Bradford Cycling Bradford Beck Living Streets Active Travel Hub | STC CE&EC Councillor Parkinson | £? |  | Long | 2023-03-27
8 Score 30 | Housing | Support people to reduce energy usage at home | 36.collate and distribute “10 Top Tips” for using less energy | Link to what already exists through (3) Social media campaign linking to existing providers | Energy Savings Trust | STC Comms Lead |  |  | Short | 2023-12-23
|  |  | 37.run info campaign on dehumidifiers | see (3) info hub Loan equipment | In Communities | CE&EC | £ ? |  | Medium | 2023-03-24
9 Score 29 | Housing | Find opportunities for Shipley buildings to generate power and transfer from gas boilers to fossil fuel free energy sources | 38.explore partnerships for all public buildings | expands on (3) and (31) | Requires working group National campaigns - signpost to them and assistance |  |  |  | Long | 2023-03-27
|  |  | 39.broker row by row/street by street scheme to insulate and change heat source | host in hub | Retrofit Saltaire - Andrew Gardner |  |  |  | Medium | 2023-03-24
|  |  | 40.comment on planning applications pushing for higher standards of energy efficiency | Influence Design Code, Local Plan and Development Plan for Bradford to include energy efficiency |  | STC P&RC check with Councillor Watson |  |  | Medium | 2023-03-24
10 Score 28 | Education | Promote report broadly and creatively | 41.disseminate widely | Hold Thanksgiving Reception to launch report Display on website Make available on event stalls at public events Discussed at Area Committee - to Exec and WYCA (attend and speak) Report progress back in Town Council Annual Report |  | STC CE&EC / Councillor McHugh / DTC / Communications Lead | 0 | Included in CJ budget | short | 2023-04-01
|  |  | 42.join up with varied groups to action recommendations | Plan configured to incorporate all collaborators Participatory budgeting process will open further
|  |  | 43.”Actors for Change” campaign on billboards/noticeboards | Jen Dyer's evaluation? 5 jurors interested £30 per poster 90cm x 80cm |  | Councillor McHugh | £150 |  | short | 2023-11-23
|  |  | 44.organise Shipley Climate Change festival | Great Big Green Week 10 - 17 June 2023 programme of events and activities and market square event Evaluate then plan 2024 event | Plastic Free Shipley Bradford Shipley Travel Alliance Fairtrade Shipley Friends of the Earth Shipley in Bloom / Bee Positive Shipley Active Travel Hub Schools College, etc | STC CE&EC plus Working Group | 0 1000 |  | Short Medium | 01/07/2023 01/07/24
|  |  | 45.develop engaging educational activities | link to (3) and run there Duke of Edinburgh Scout & Guide movement Woodcraft groups | Nifty Sustainability KT Permaculture Youth Service | Eddie Webb |  |  | Medium | 2023-03-24
11 Score 21 | Transport | Encourage car sharing | 46.bookable non-profit e-car pool | link to (3) with owners leaving details research availability with CBMDC & employers | Enterprise car hire scheme Bradford Shipley Travel Alliance - Ludi Simpson? | STC CE&EC |  |  | short (research) long (implementation | Nov-23 Mar-27
Score 17 | Transport | Encourage switch to electric cars | 47.provide information re charging | find out where CBMDC ones are in Shipley for Town Council website |  | STC CE&EC |  |  | short | 2023-12-23
|  |  | 48.greater provision of electric car charging points | comment on planning proposals lobby for suitably located increased provision |  | P&RC |  |  | ongoing